## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
c01 | Open Accounts | As a user, I want to open one or more different kinds of accounts so that I can manage my income and expense from different people and different kinds of organisations and increase the level of property security. | 1 | 1 | 1. There are three kinds of account for customers to choose: Saver account; current account and Junior account 2. The main function of these accounts are similar. | Different accounts has different attributions and methods-Saver accounts have notice date and notice amount; current accounts have overdraft limit. | 2018-04-16 | 2018-04-22
c02 | Add new customer | As a user, I want to register by entering necessary information when I first use the the bank system. So that I can log in everytime I use the system instead of entering my information again and again. | 1 | 1 | 1. When users register, they need to enter their name, address and date of birth. 2. Users can choose a type of accout to be opened after their information has been checked with no error. | Only customers under the age of 16 may open a Junior account. To determine the credit status of a customer, the bank sends the customer's details to a Credit Agency, who then carries out a credit search. Provided that the customer has a satisfactory credit history, a new account is opened. | 2018-04-16 | 2018-04-22
c03 | Account security | As a user, I want to set a password (PIN) when I create an account. So that my property security can be ensured. | 1 | 1 | 1. When user first create an account, they need to enter a password. Each time they want to check the account, they need to enter the correct password. | 1. Each accout has its own password seprately. 2. Passwords cannot be reset in this bank system. | 2018-04-16 | 2018-04-22
c04 | Deposit cash | As a user, I want to deposit funds in my account reliably. So that the property security can be ensured and I can use the money for future investment. | 1 | 2 | 1. Create a class-deposit which is the subclass of Transaction. 2. Store the amount of money, the date of the day create this deposit and whether the money has been cleaned by setting some attributes. | 1. Deposit is a class extends Transaction with attribution- a boolean value represented clear status. 2. Besides of extends costructor from superclass, it can create the transactionID start with “deposit". | 2018-04-23 | 2018-04-29
c05 | Withdrawal funds | As a user, I want to withdrawal my funds from my account any time and any places. So that I can use my money for other activities. | 1 | 2 | 1. Create a class-Withdrawal which is the subclass of Transaction. 2. Store the amount of money, the date create this deposit by setting some attributes. | 1. Besides of extends costructor from superclass, it can create the transactionID start with “Withdrawal". | 2018-04-23 | 2018-04-29
c06 | Set a limit of the amount of money to withdrawal | As a user, I want the bank to set a limit of the amount of money when receiving withdrawal request. So that when accidences happend, such as my account has been stolen, the overlimited withdrawal can be prevented. | 2 | 3 | 1. In current account, the limit of the amount of money to withdrawal is the balance in this account add to the overdraft limit. 2. In saver and junior account, the limit of the amount of money to withdrawal is just the balance in this account. | In Current Account, there is an attribution-overdraftlimit. It is allowed for users to withdrawal money less than balance added with overdraftlimit. | 2018-04-30 | 2018-05-06
c07 | Set a minimum period of notice to withdrawal in Saver account | As a user, I want to set a minimum period of notice in my Saver Accounts. So that the period my funds stored in my Saver Account can be ensured. | 2 | 4 | 1. In withdrawal class, set an attribute-notice date when customer first create the Saver account. 2. There is also a method to calculate whether the period between current time and the notice date has over 7 days. | When comparing the period between current date and notice date, the methods change the information in date form into seconds to calculate. | 2018-05-07 | 2018-05-13
c08 | Special Account for Minority | As a user, I want to set a special kind of account for minority, who under the age of 16. So that the minority can have the right to open their own account and learn how to manage their allowance. | 2 | 1 | 1. The subclass of Account-junior account, which is designed for minority with similar functions as other two kinds of accounts. | Before users open junior accout, the age will be calculated according to the birthday they entered when register. Only when the calculation result is under 16, the account can be created successfully. | 2018-04-16 | 2018-04-22
c09 | Use multiple methods to pay the deposit | As a user, I want to use multiple methods to pay the deposit, such as in cash or by cheque. So that I can manage my funds for flexiblely. | 3 | 3 | 1. There are 2 ways to pay the deposit: cash and cheque. 2. We set a boolean attribute in deposit class: cleared, which refers to whether the customer pay the deposit by cash. If the deposit is paid by cheque, the boolean value is false and the balance will not change. | Users can choose the way to pay the deposit, then the credit status and this transaction can be recorded | 2018-04-30 | 2018-05-06
c10 | Clear Funds | As a user, I want to clear funds sever days after I deposit money. So that I can update by balance which is refreshed and calculated as soon as possible. | 3 | 4 | There are two occasions where users can clear funds: 1. When deposit in cash; 2. After they deposit by cheque, if users check the transaction detail, they will be asked to clear deposit. | Once user clear account, the clear status and balance will be refreshed. | 2018-05-07 | 2018-05-13
c11 | Suspend Account | As a user, I want to suspend my account in some situations and no further transaction can be made. So that my property security can be ensured. | 4 | 5 | 1. Set a boolean attribute refers to the suspend situation. 2. Design a method for customers to change the suspend status. | Once the account has been suspended, there is nothing can be operated in this account. | 2018-05-14 | 2018-05-20
c12 | Close account | As a user, I want to close account provided that the balance has been cleared. So that I will not need to worry about some property security any more. | 4 | 5 | 1.Set a boolean attribute refers to the close situation. 2. Design a method for customers to change the close status and remove the account out of arraylist. | Closing account is an operation which cannot be canceled. | 2018-05-14 | 2018-05-20